## ToDo
Module | Task | Estimate
Engine | Refactor index based unique container. Think about using size_t rather than unsinged int. | 2
Engine | Move to pre-compiled shaders | 5
Engine | Bounding sphere occlusion | 4
Engine | FSAA | 2
Rorn Pool | Build basic app | 2
Rorn Pool | Game initialisation (position of balls, etc) | 14
Engine | Basics of a physics engine | 35
Rorn Pool | Player can move the cue ball (when appropriate) | 5
Rorn Pool | Player can move cue | 5
Rorn Pool | Player can take a shot | 10
Engine | Compiled shaders | 5
Model Compiler | Model compiler refactoring - wait till we have two surface formats implemented | 21
Model Compiler | Error handling strategy in Model Compiler - possibly use xsd? | 21
Maths | Complete the Rorn Maths library | 35
Engine | Revise, understand and document the view and projection matrix builds | 7
Engine | Add full screen support | 3
Note on B12: Jonny: Do we need shaders to be compiled into models? Think about pros and cons.
Note on B15: Jonny: Build a load of degenerate scene files and write unit tests to ensure everything is trapped.