## ToDo
Module | Task | Estimate
Engine | Add input manager with keyboard and mouse | 6
Model Viewer | Add camera controls to model viewer | 3
Engine | Point lights | 21
Engine | Point lights in model chain | 7
Engine | Bounding volume occlusion | 7
Rorn Pool | Build basic app | 3
Rorn Pool | Game initialisation (position of balls, etc) | 14
Engine | Basics of a physics engine | 21
Rorn Pool | Player can move the cue ball (when appropriate) | 5
Rorn Pool | Player can move cue | 5
Rorn Pool | Player can take a shot | 10
Engine | Compiled shaders | 5
Scene Exporter | Make exporter a GUP. Build UI & hook data into the max files | 14
Scene Exporter | Make the path from Max->Model Viewer seamless | 4
Model Compiler | Model compiler refactoring - wait till we have two surface formats implemented | 21
Model Compiler | Error handling strategy in Model Compiler - possibly use xsd? | 21
Maths | Complete the Rorn Maths library | 35
Engine | Revise, understand and document the view and projection matrix builds | 7
Engine | Add full screen support | 3
Scene Exporter | Get 64-bit scene exporter working | 7
Note on B5: Jonny: We possibly need to think about some sort of 'game object' editor that includes lights, physics primitives, etc. Otherwise it's just a case of pushing it through max.
Note on B13: Jonny: Do we need shaders to be compiled into models? Think about pros and cons.
Note on B18: Jonny: Build a load of degenerate scene files and write unit tests to ensure everything is trapped.